Sussex LNRS Working Group

Meeting Notes

Monday 20 May 2024, 11:00 to 13:00

Present: ESCC, WSCC, SDNPA, WayForward, HWAONB, SWT, BHCC, SxBRC, Knepp, EA, CBC, WSCC, CJH Farm Advice/SE FWAG, HDC, CLA, MSDC, SxNP, NE, HDC, FC, ESCC, ESCC

Apologies: RDC, WDC, HDC, FC

- Welcome, Introductions and Apologies

ESCC welcomed everyone to the meeting. ESCC to Chair.

- Minutes and matters arising

Minutes accepted and no matters arising.

All actions from last meeting are completed/covered in this meeting.

- General Update

Defra:-

- Mapping potential measures guidance has been published.

- Awaiting release of the purchase orders. In a good place budget-wise.

Project planning: good progress. Pre-consultation will go out to this group by Christmas:-

- WBS1 – all completed.

- WBS2 – APIB completed bar a few issues. Description is in development, informed by the completed plans and strategies, and trends, threats and pressures pieces.

- WBS3 – ongoing stakeholder engagement services being secured via WayForward. Working towards engagement with farmers/landowners (large-landed estates and farm clusters) and youth (East/West Sussex Youth Cabinets). Will attend a CLA conference and NFU event. Two county-level workshops in June. Public survey responses are going up, as are previous webinar and video views.

Project mapping tool: complete and due to be live by the end of this week.

Species: there will be a Species T&FG meeting on 5th June. A draft long list has been compiled.

Marine: ongoing liaison with Sussex Bay and their Seascape Restoration Strategy. The national marine LNRS group has been dissolved but it could be revived.

- Update on Stakeholder Engagement

Draft slides for June webinars

This presentation is a key point in the engagement calendar for the public.

Discussion

The APIB map is too complicated to show in the slides but it will be described during the presentation.

It’s worth conveying the importance of habitat mosaics between key priority habitats.

It may be worth adding deer management groups to the landowner engagement activities.

- Discussion around Priorities

Exercise on shortlisting priorities.

- Next Steps (Chair)

Summary of actions from above:

- Add SDNPA to farm cluster meetings.

- Share the project mapping tool once live.

- Circulate species T&FG meeting invitation.

- Add Knepp/W2W to species T&FG meeting.

- Keep BHCC linked into the Savills group meeting.

- Have a look at Environmental Farmers Group.

- Ensure that Knepp and SDNPA is included in landowner engagement activities.

- Discuss landowner engagement with Knepp.

- Send physical hardcopy of flyers to SDNPA.

Priority: unpick the above exercise and feedback to the next WG meeting.

- AOB

Habitat banking report for BHCC is in its draft form.

All to promote June webinars.

DONM: 17 June 2024, 11:00-13:00